1. Given:

| Activity | Predecessors |
| --- | --- |
| A | None |
| B | None |
| C | None |
| D | A,B |
| E | B,C |
| F | D |
| G | E,F |

Draw the network table for this project.  Be sure to show the start and end node.

2.  Given:

Activity	Time (Days)

A		5

B		3

C		4

D		1

E		4

F		3

G		2

In each node, you MUST show EST, EFT, LST, LFT, SLACK TIME.  You must also indicate the total duration of this project.  You must also indicate the critical path.

Draw a new picture.  Do not use the picture above.

3.  Given:

| Activity | Time | EST | EFT | LST | LST | Slack |
| --- | --- | --- | --- | --- | --- | --- |
| A | 5 | 0 | 5 | 0 | 5 | 0 |
| B | 6 | 5 | 11 | 6 | 12 | 1 |
| C | 2 | 5 | 7 | 16 | 18 | 11 |
| D | 9 | 5 | 14 | 5 | 14 | 0 |
| E | 9 | 11 | 20 | 12 | 21 | 1 |
| F | 3 | 14 | 17 | 18 | 21 | 4 |
| G | 7 | 14 | 21 | 14 | 21 | 0 |
| H | 4 | 14 | 18 | 18 | 22 | 4 |

Assume the cost per week for A, B, C, G, H is 1.

Assume the cost per week for D is 2.

Assume the cost per week for E is 3.

The cost for week 1 of F is 9, week 2of F is 8, week 3 of F is 7.

(a) Develop an EST budget.  Show cost per week as well as cumulative cost. You may not need all the rows and all the columns.

| Activity | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total For Week |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cumulative Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Develop an LST budget.  Show cost per week as well as cumulative cost. You may not need all the rows and all the columns.

| Activity | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total For Week |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cumulative Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

4. Given:

| A | B | C | D | E | F | G |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Activity | Budgeted Cost | Percent Complete | Actual Cost | Value of Work Completed | Actual Cost Minus Value of Work Completed |
| 2 | A | 20,000 | 100% | 26,000 |  |  |
| 3 | B | 12,000 | 100% | 15,000 |  |  |
| 4 | C | 28,000 | 60% | 27,000 |  |  |
| 5 | D | 25,000 | 75% | 30,000 |  |  |
| 6 | E | 10,000 | 30% | 11,000 |  |  |
| 7 | F | 8,000 | 60% | 4,000 |  |  |
| 8 | G | 12,000 | 0% | 0 |  |  |
| 9 | H | 10,000 | 0% | 2,000 * |  |  |
| 10 | TOTALS |  |  |  |  |  |

H required an advance deposit.

Fill in the last 2 columns of the table.  Then, determine if the project is OVERBUDGET or UNDERBUDGET.

Write the EXCEL formula needed to compute cell F6.  .

Write the EXCEL formula needed to compute cell G6.

In the following questions: if a situation is impossible, explain why.

5. Given the following information for node X:   EST = 4, EFT = 12, LFT = 15

What is the DURATION of node X?

What is the LST of node X?

What is the slack of node X?

Is node X on the critical path?  Explain why or why not.

6. Given the following information for node X:   EST = 6, EFT = 9, LST = 4

What is the DURATION of node X?

What is the LFT of node X?

What is the slack of node X?

7. Given the following information for node X:   EST = 5, EFT = 9, LST = 8, LFT = 11

What is the DURATION of node X?

What is the slack of node X?

8. Given:

| ACTIVITY | NORMAL DURATION | NORMAL COST | CRASH DURATION | CRASH COST | CRASH COST PER WEEK |
| --- | --- | --- | --- | --- | --- |
| A | 6 | 3,000 | 5 | 8,000 |  |
| B | 5 | 5,000 | 3 | 6,000 |  |
| C | 9 | 7,200 | 7 | 8,800 |  |
| D | 4 | 3,600 | 2 | 5,200 |  |

Fill in the CRASH COST PER WEEK COLUMN. Show work.

9. Given:  There are two critical paths in your network.   A - C - E – H   and    A – B – E – G

Here are the weekly crash costs

A – 900

B – 180

C – 200

D – 150

E – 150

F -- 100

G – 700

H – 350

None of these activities can be crashed by more than ONE week.

Which node(s) would you choose to crash this project by 1 week?  Why?

Assuming you crashed the project by ONE week and both critical paths remained the same.  Remember, the activity(s) you chose in the first part of the question can not be used again.  Which node(s) would you choose to crash this project by another week?  Why?

Assuming you crashed the project by ONE week and both critical paths remained the same.  Remember, the activity(s) you chose in the previous parts of the question can not be used again.  Which node(s) would you choose to crash this project by another week?  Why?