## Basic Template
Big Game Project --- template for distribution of tasks to ensure smooth teamwork
major objectives: |  |  |  |  | major tasks: | PROJECT COMPLETION DATE: DEC 11, 2012 | [6 empty] | who does what
|  |  |  | 1 | game proposal
|  |  |  | 2 | storyboards (design)
|  |  |  | 3 | rules of play and scoring (design)
|  |  |  | 4 | game objects (define)
|  |  |  | 5 | game loop (design)
|  |  |  | 6 | game play state machine (design)
|  |  |  | 7 | game objects: graphical design
|  |  |  | 8 | game objects: behavior designed
|  |  |  | 9 | game objects: behavior coded
|  |  |  | 10 | game objects: behavior tested
|  |  |  | 11 | game levels designed (if applicable)
|  |  |  | 12 | game levels coded (if applicable)
|  |  |  | 13 | game levels tested (if applicable)
|  |  |  | 14 | user interface: graphical design
|  |  |  | 15 | user interface: code written
|  |  |  | 16 | user interface: initial testing
|  |  |  | 17 | audio assets: designed/selected
|  |  |  | 18 | audio assets: integrated in game
|  |  |  | 19 | play testing by project team members
|  |  |  | 20 | play testing by classmates
|  |  |  | 21 | draft final presentation
|  |  |  | 22 | design demo
|  |  |  | 23 | rehearse demo
24
25
design review (20-nov) | code review (4-dec) | play testing (6-dec) | final demo (11-dec) |  |  | 2012-11-15 | 2012-11-20 | 2012-11-27 | 2012-11-29 | 2012-12-04 | 2012-12-06 | 2012-12-11 | team member name: | team member name: | team member name:
adapted from: http://www.onepageprojectmanager.com and http://www.evl.uic.edu/spiff/class/cs426/Notes/CS426_OPPM_Template.xls
major tasks
=
major objectives
class dates to target
key: